## Requirements Register
Requirement ID | Category | Requirement Statement | Source / Rationale | Priority | Verification Method | Acceptance Criteria / Evidence | Status | Owner | Trace / Dependency | Notes
REQ-F-001 | Documentation | The project shall maintain a requirements register in which each requirement has a unique identifier. | Task order dated 22-Oct-2026; traceability and control objective | High | Inspection | Every active requirement has a non-duplicate ID. | Candidate | Systems Requirements Engineer | P01 scope baseline | Initial candidate; confirm with project owner.
REQ-F-002 | Requirements Quality | Each requirement shall describe one obligation or capability using clear and unambiguous language. | Requirements quality practice | High | Review/Inspection | Reviewer can interpret the requirement without conflicting meanings. | Candidate | Systems Requirements Engineer | REQ-F-001 | Review for atomicity and ambiguity.
REQ-F-003 | Traceability | Each requirement shall record its source or be explicitly marked as an engineering assumption when no approved source is available. | Task order; traceability objective | High | Inspection | Source field is populated or assumption is explicitly identified. | Candidate | Systems Requirements Engineer | P01 assumptions | Do not label assumptions as approved customer requirements.
REQ-F-004 | Verification | Each requirement shall have a proposed verification method or be marked TBD pending clarification. | Task order: acceptance criteria and verification methods are planned for 23-Oct | High | Inspection | Verification method is populated or TBD is recorded with an action. | Candidate | Verification Engineer | REQ-F-001 | Methods may include test, analysis, inspection, or demonstration.
REQ-F-005 | Configuration Management | Changes to baselined requirements shall be recorded with a revision, date, reason, and approval status. | Task order: configuration-control procedure is planned for 26-Oct | High | Inspection | Change history records the required fields for each approved change. | Candidate | Configuration Engineer | P01 configuration information | Detailed workflow to be defined in P10.
REQ-F-006 | Open Issues | Unresolved assumptions, dependencies, and questions shall be maintained in a reviewable list. | Task order: open questions and assumptions deliverable planned for 24-Oct | Medium | Inspection | Each open item has a description and an owner or action where known. | Candidate | Systems Requirements Engineer | P06 planned | Assign owners after team confirmation.
REQ-NF-001 | Maintainability | Project requirement records shall use consistent field names and controlled status values. | Maintainability and reviewability objective | Medium | Inspection | All rows use the agreed register structure and status vocabulary. | Candidate | Configuration Engineer | REQ-F-001 | Suggested statuses: Candidate, Under Review, Approved, Rejected, TBD.
REQ-NF-002 | Document Control | Each submitted baseline document shall display a document ID, revision, date, and status. | Task order: traceability and configuration control | Medium | Inspection | Required document-control fields are visible in each deliverable. | Candidate | Configuration Engineer | P01 | Apply to subsequent deliverables.
REQ-SYS-001 | System Definition | The project owner shall confirm the system boundary, intended users, operating context, and external interfaces before requirements are baselined. | Open clarification needed because detailed project description was not supplied with screenshot | High | Review | Review record confirms system boundary, users, context, and interfaces or records unresolved items. | Open Action | Project Owner | P01 open questions | Action: obtain and review the official project description.
REQ-SYS-002 | Performance | Any project-specific performance thresholds shall be taken from an approved source; otherwise the value shall be recorded as TBD. | Prevent unsupported numeric assumptions | High | Inspection | Each numeric threshold has a source or is marked TBD. | Candidate | Systems Requirements Engineer | REQ-F-003 | No performance values were provided in the screenshot.
REQ-SYS-003 | Safety / Compliance | Applicable safety, environmental, and regulatory constraints shall be identified and recorded when the system context is confirmed. | Aerospace/robotics context is provisional; exact system unknown | High | Review | Applicable constraints are listed with source, or an open action remains. | Open Action | Project Owner / Safety Lead | P01 open questions | Do not infer a specific standard without confirmation.
REQ-IF-001 | Interfaces | External interfaces shall be documented with interface name, direction, data/physical characteristics, and source where applicable. | Interface identification is part of scope baseline | Medium | Inspection | Each identified interface has the listed fields or a documented TBD. | Candidate | Interface Engineer | System boundary confirmation | Populate after architecture/context review.

## Assumptions & Actions
ID | Type | Description | Impact if Unresolved | Action / Next Step | Owner | Status
A-001 | Assumption | RE-T1 is the project identifier. | Document naming and traceability may be wrong if identifier differs. | Confirm against official task brief. | Project Owner | To Confirm
A-002 | Assumption | This is an initial training-level systems engineering package. | Scope may omit project-specific engineering deliverables. | Confirm assignment expectations. | Teacher / Project Owner | To Confirm
A-003 | Assumption | Detailed product description was not available in the supplied screenshot. | Candidate requirements may need revision. | Obtain and review full project description. | Systems Requirements Engineer | Open
Q-001 | Question | What is the exact system purpose and intended mission? | Cannot fully baseline scope. | Ask project owner / review project brief. | Systems Requirements Engineer | Open
Q-002 | Question | Which standards and safety constraints apply? | Compliance scope remains unknown. | Confirm system domain and applicable standards. | Project Owner / Safety Lead | Open
Q-003 | Question | What acceptance thresholds and verification evidence are required? | Verification planning cannot be finalized. | Extract values from approved source documents. | Verification Engineer | Open